## Planificador de proyectos
Planificador de proyectos
Milestone | Task | Start | Final | % Completed | WEEKS
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Definiton of the project | Objectives, planning and Roles | 1 | 1 | 100% | bar: WEEKS 1
| Technical proposal | 1 | 2 | 100%
| Presentation 0 | 2 | 1 | 100%
Development | Infrastructure | 3 | 3 | 100% | bar: WEEKS 3
| Exterior. Node AirQ | 3 | 2 | 30% | bar: WEEKS 3 to WEEKS 5
| Inside. Node AirQ | 4 | 2 | 30% | bar: WEEKS 3 to WEEKS 5
| Container Node | 5 | 2 | 30% | bar: WEEKS 5 to WEEKS 7
| Parking node | 6 | 2 | 0% | bar: WEEKS 5 to WEEKS 7
| Server | 7 | 3 | 40% | bar: WEEKS 6 to WEEKS 9
| Mechanical parts | 3 | 3 | 10% | bar: WEEKS 7 to WEEKS 12
Assembly | Test | 12 | 3 | 0% | bar: WEEKS 13 to WEEKS 15
Final Sprint | Documentation | 15 | 3 | 0% | bar: WEEKS 9 to WEEKS 17
| Final Presentation | 16 | 2 | 0%